## APQP_Status
GSM-F032 - APQP Status Form
Date of Issue: | [12 empty] | Form Number:
Supplier | [9 empty] | Date
Location | [9 empty] | Review #.
Supplier Code | [9 empty] | Project / Part Name
Risk Assessment | [9 empty] | Specification/Drawing #:
New : |  | Site |  | Technology |  |  | Process |  |  | Spec/Draw Revision Level
|  | Other Risks | [7 empty] | User Plant (s)
Team Members |  |  |  |  | Company/Title | [5 empty] | Phone # |  | E-mail Address
Build Level Prototype |  |  | Required Date |  |  |  | Quantity |  |  | Special Characteristics |  | Comments
APQP Elements | [5 empty] | GYR | G | Program | Supplier | Closed | Champion | Document | Remarks or Contingency Plans Required
[6 empty] | Status | Y | Need | Timing | Date | Name | Revision
[7 empty] | R | Date | Date |  |  | Date & Rev.
Phase 1.0 : Plan & Define Program
1) Sourcing Decision
2) Purchase Order / Contract
3) Solero Technologies requirements & needs understood
- Design Goals (if applicable) (1.7)
- Preliminary Process Flow (1.10)
- Product Assurance Plan (1.12)
- Review Lessons Learned
4) Timing Plan (1.0)
Phase 1.0 Gate Review & Sign Off | PHASE 1 GATE REVIEW & SIGN OFF
Phase 2.0 : Product & Design Development
5) Design FMEA (if applicable) (2.1)
6) Design Review(s) (if applicable) (2.3)
7) Design Verification Plan (if applicable) (2.4)
8) APQP Status Sub-Supplier
9) Facilities, Tools, and Gages
- new equipment, tooling and facilities requirements (2.10)
- gage / test equipment requirements (2.12)
- special product / process characteristics (2.11)
10) Prototypes Control Plan (if req'd) (2.5)
11) Prototype Builds (if req'd) (2.5)
12) Drawings and Specifications (2.6,2.7)
13) Team Feasibility Commitment (2.13)
Phase 2.0 Gate Review & Sign Off | PHASE 1 GATE REVIEW & SIGN OFF
Phase 3.0 : Process & Design Development
14) Process Flow Chart (3.3)
- floor plan layout (3.4)
15) Process FMEA (3.6)
16) Measurement Systems Plan
- measurement systems analysis plan (3.9)
- preliminary process capability study plan (3.10)
17) EPC Control Plan (3.7)
- heat treatment assessment (if applicable)
- product identification & traceability plan
18) Process Instructions (3.8)
- Tooling & Equipment maintenance management plan
- employee skill maintenance / training plan
- Operator documentation / instructions
Phase 3.0 Gate Review & Sign Off
Phase 4.0 : Product & Process Validation
19) Packaging Evaluation (4.6)
20) Production Process Control Plan (4.7)
21) Production Trial Run (4.1)
- We are Ready (WAR) Audit
- Run at rate for capacity
- Measurement System Evaluation (4.2)
22) Preliminary Process Capability Study (4.3)
23) Production Validation Testing (4.5)
24) Production Part Approval (PPAP) (4.4)
- PPAP Submission
- PPAP Approval
25) Quality Planning Sign Off (4.8)
Phase 4.0 Gate Review & Sign Off
Phase 5.0 : Production
26) Verification of Performance Sustainability
Phase 5.0 Gate Review & Sign Off
- COMMENTS
Required Form
Revision Level: April 7th, 2015
Note on B18: APQP Team Participants; Supplier, Sub-tier suppliers, and BorgWarner Personnel, including all affected Plants.
Note on P30: Define the Number of Special Characteristics; that may be customer specific; including: "Significant" "Major" "Critical" "High Impact" that requires on-going statistical capability and / or requires validation in the Process Control Plan .
Note on R40: The current revision & date for the applicable document
Note on S40: Contingency plans are required for any element that has a yellow or red status.
Note on L40: Status = Green, Yellow or Red as defined in definitions tab Numbers in this column correspond to the AIAG APQP manual definitions (i.e.. 1.7 refers to Design Goals)
Note on B52: What: A review of all the objective evidence relative to the phase of the program being reviewed The Gate reviews are program milestones, and must be tracked to confirm program timing is maintained Action: All prior steps must be “Green” prior to gate sign off Action plans must be identified for any element not green, and elevated as necessary Team consensus is required but ultimately it’s the SDE who signs Objective Evidence: Gate review will be audited, based on BU specific requirements TS - TBD MT/TH - SSO Process Turbo Emissions - TBD TTS - TBD Owner: Supplier Development & BU auditor
Note on J98: What: The final review & Closure of the program launch Action: The review and agreement of the supplier’s ability to sustain the production performance requirements Objective Evidence: Gate review will be audited, based on BU specific requirements TS - TBD MT/TH - SSO Process Turbo Emissions - TBD TTS - TBD Owner: Supplier Development & BU auditor
Note on B44: What: Formal commitment to work with the Supplier on the Program Action: BW team consensus needed on sourcing decision BW Purchasing informs supplier of intent to move forward Objective Evidence: Approved Source Selection Document – (source selection form or letter of intent) Owner: Purchasing
Note on B46: What: Ensure that BW’s quality and design objectives are understood as well as overall supplier management practices Action: EPC review & Identification of expectations Review supplier manual & verification of training completed Supplier and BW will have technical reviews of the prints (special & pass through characteristics), discuss volumes, and any other requirements Address all know defects on similar products. Focus on prevention, detection and process capability Objective Evidence: Signed APQP Kick-off checklist Documented the supplier has completed the Supplier manual E-training Documented items under #3/ currently under timing plan Set Goals: Design, Reliability and Quality Preliminary BOM, Process Flow, Special CC’s Product Assurance plan – signed EPC form? Review lessons learned– Address all know defects on similar products. Focus on prevention, detection and process capability + this supplier CPM’s Owner: Supplier Development
Note on B51: What: A documented plan identifying all the required deliverables & timing to meet SOP requirements. Action: Develop a timing plan identifying all the APQP elements as well as significant events in the program. Objective Evidence: A documented timing plan – living document, to be updated as necessary Owner: Supplier / Supplier Development
Note on B57: What: The supplier must do APQP with its suppliers Action: Supplier will do a Risk Assessment of every supplier where applicable (high risk). High impact suppliers should have structured APQP BW SDE to review the supplier’s sub-tier supplier risk assessments concurring on the risk and criticality rating of the sub-tier suppliers. Supplier Implement regular APQP reviews with sub-tier supplier. Depending on the significance of the supply chain, BW may require an on-site visit at the sub-tier supplier. The frequency of these updates will be determined by BW based on the risk / impact of the sub-tier supplier. Objective Evidence: Sub-Tier Risk Assessment APQP implemented with high impact Sub-suppliers Owner: Supplier and Sub-supplier Engineering, Purchasing, Manufacturing and Quality
Note on B58: What: Document that all the tools and gauges are in place and fully functional at time of prototype production runs Action: Determine gauge and test equipment requirements, especially for special product and process characteristics All requirements to support program should be defined for supplier and sub-suppliers. Timing shall be defined in the timing plan for all Facilities, Tools, and Gages. Objective Evidence: A detailed list of all equipment & tooling is provided along with facility plan. This list includes the current status of the equipment (Existing, Rebuild required, Relocation of equipment, To be Purchased). Appropriate items to be documented in the timing plan, as well as any planned changes for capacity or future business expansion. A detailed list of all Gauges & Test equipment is provided. This list includes the current status of the Gauges & equipment (Existing, Rebuild required, Relocation of equipment, To be Purchased). Appropriate items to be documented in the timing plan. These tasks should include how to ensure common gauging (type & supplier) will be used to achieve appropriate gage correlation. Completed "Special - Pas Thru List" on tab of APQP status report Owner: Supplier and Sub-supplier
Note on B65: What: Agreement by Design and Manufacturing that the released design is feasible to manufacture Action: Development Engineering will assess the design and resolve any manufacturability issues prior to design release The team feasibility must be completed for the latest part revision level, even if supplier is NOT design responsible. Objective Evidence: A Completed team feasibility commitment form (included in APQP Status Report GSM-003) signed by the supplier. Owner: Supplier
Note on B70: What: A tool for determining and ranking all possible failure modes, their effects and causes Action: A cross functional production quality team (ME, IE, Operators…etc) develops the PFMEA starting with input from the DFMEA. The DFMEA should be used to identify potential failure modes and assign severity levels Include “Lessons Learned” to ensure "Failure Modes" are included for all known / experienced "defects". Review BW and or similar product’s “lessons learned” & CPM’s. All manual operations (including load & unload) must consider "missed operation" as a failure mode Failure modes associated with contamination or corrosion must identified Objective Evidence: Completed PFMEA document reviewed and if applicable approved by BorgWarner The PFMEA must be update to include all the failure modes as they are discovered during the product life cycle Owner: Supplier
Note on B74: What: Production control plan plus additional controls during launch. EPC “Early Production Containment” is derived from this document Action: Based on the PFMEA and other known risks the EPC plan will be developed by the supplier and approved by BW. The EPC plan will define additional controls and key features to monitor while experience is gained on the “Infant Process” Coordinate common verification to BW EPC receiving audits. “Supplier Better be checking what BW is checking” Begin developing visual boundary samples Supplier report EPC performance results to drive EPC exit Perform CQI-9 Heat Treatment Audit if HT is required Defined plan to achieve traceability of material Objective Evidence: EPC Control Plan Completed CQI-9 Audit of Supplier & Sub-Tier Supply base Part traceability plan Owner: Supplier / BW SDE
Note on B84: What: It is a detailed list of checks, tests, and measurements along with the inspection frequencies and reaction plans for each specific process step. Action: Supplier will develop the document insuring that all current controls listed in the FMEA are included Ensure that Final / Dock audits are included, and that all known & experienced defects are prevented or contained / controlled. Verify work/process instructions have been updated to reflect the lessons learned during the EPC process Objective Evidence: Production control plan per AIAG standards Owner: Supplier Review by BW SDE
Note on B87: Perform Run @ Rate to verify production process meets BW Contracted capacity (not scheduled capacity). This should include critical Sub-Tier suppliers
Note on B45: What: Purchasing commitment with Terms & Conditions Action: Obtain a confidentiality agreement with supplier Agree on quality performance & liability requirements BW Issues a P.O. Objective Evidence: Signed PO or alternate document showing acceptance to Terms & Conditions Signed confidentiality agreement on file Signed quality performance & liability agreement (if required) Owner: BW Purchasing & Supplier
Note on B54: What: Determines the maximum number of potential failures that could occur functionally from a design standpoint Action: Develop the DFMEA. Action plans are required for any high RPN’s (see customer specific requirements). Regardless of the RPN rating, continuous RPN reduction should be ingrained in the supplier/BW process Objective Evidence: If Applicable (supplier is design responsible), the Supplier DFMEA is completed reviewed by BW Product Engineering and on file If Not Applicable, BW will assist in defining the severity ratings & failure modes for the supplier's PFMEA. The BW DFMEA is NOT to be provided to the Supplier Owner: Supplier Engineering (supplied design) & BW Engineering (joint or provided design)
Note on B56: What: DVP is the Engineering test and evaluation plan to determine if the design is fit for use Action: Document & Communicate Tests & Pass/Fail Requirements. The plan must clearly identify who is responsible to complete each test & the timing for these tests. Supplier/BW Engineering will use a project tracking tool to setup, maintain and complete the required testing Objective Evidence: Completed Design Verification Plan (DVP) & approved by BW Product Engineering Owner: Supplier Engineering (supplied design) BW Engineering (joint or provided design)
Note on B59: A detailed list of all equipment & tooling is provided along with facility plan. This list includes the current status of the equipment (Existing, Rebuild required, Relocation of equipment, To be Purchased). Appropriate items to be documented in the timing plan, as well as any planned changes for capacity or future business expansion.
Note on B60: A detailed list of all Gauges & Test equipment is provided. This list includes the current status of the Gauges & equipment (Existing, Rebuild required, Relocation of equipment, To be Purchased). Appropriate items to be documented in the timing plan. These tasks should include how to ensure common gauging (type & supplier) will be used to achieve appropriate gage correlation.
Note on B61: Completed "Special - Pas Thru List" form attached
Note on B62: What: Must have a documented process and inspection plan for each prototype run Action: Supplier, SDE, & BW Product Engineering reach consensus on prototype materials, process, & dimensional documentation requirements Document the materials, gauges, sampling frequency, tools, and equipment. Determine what requirements (capabilities if applicable) are needed for Special characteristics and other dimensions & error proofing for Pass through characteristics Objective Evidence: Documented Process, Inspection results, & inspection gauging The dates and rating on the APQP status report is based on the 1st batch of prototypes. Subsequent submission will be tracked on the overall program timing plan. The intent of this element rating is to establish that the supplier understands and can meet the expectations of the prototype requirements Owner: Supplier (could be different than production Supplier)
Note on B63: What: Deliver parts that meet the agreed prototype requirements Action: Communicate the Prototype QTY & Timing requirements Prototypes are produced by the supplier in accordance to the agreed upon prototype process & inspection plan Dimensional data is documented and submitted with prototype parts to BorgWarner BorgWarner approval is required for all non conformances Document any issues or lessons learned with the prototypes in the Open issues list Objective Evidence: Prototype parts, Dimensional Results, & Updated open issues list (if required) The dates and rating on the APQP status report is based on the 1st batch of prototypes. Subsequent submission will be tracked on the overall program timing plan. The intent of this element rating is to establish that the supplier understands and can meet the expectations of the prototype requirements Owner: Supplier & APQP Team
Note on B64: What: Release Drawings & Specifications Action: Production part print & specifications released from BW and received by the supplier Objective Evidence: BorgWarner Production print & specification released in the BorgWarner system Verification Supplier has received the latest revision and can release production tooling, gauging & fixtures Owner: BW Engineering / GSM & Supplier
Note on B68: What: A chart that represents the manufacturing process. It should be specific and detailed showing the exact process going into production Action: A cross functional team will assess the process and analyze sources of variation The Process flow chart must match in each operation the PFMEA and the Control Plan. Objective Evidence: A Documented Process Flowchart, best practice flow charts include: Process Step (s) Transportation method (s) Inspection Station (s) External process (es) Optional, Back-up, or Rework process (must be PPAP'd) A floor plan layout is also recommended, and should include the following; Layout of production area Raw Material Flow of Material Equipment & gauging Work in process material Finished goods # of operators & stations Owner: Supplier
Note on B69: Layout of production area - Raw Material - Flow of Material - Equipment & gauging - Work in process material - Finished goods - # of operators & stations
Note on B71: What: A plan to ensure gauge linearity, accuracy, repeatability, reproducibility & correlation between BorgWarner (BW & Customer) and the Supply base (supplier & sub-tier suppliers). Action: Define which characteristics & gauges require Gage R&R capabilities and other customer specific requirements. Confirm the gauge R&R studies for all gauging are performed on the BorgWarner part or similar tolerance part (if approved by BW). Define gauge methods for each attribute including error proofing (as necessary) Define which characteristics BW requires initial and or ongoing capability. Capability of each tooling, cavity, machine, etc must be consider when developing a Measurement system plan. Communicate to the supplier the TS 16949 third party accredited lab certification requirements Ensure no gauge equipment or fixtures are ordered until the measurement plan has been agreed to by BorgWarner. Objective Evidence: An approved list of gauge equipment & fixtures for all attributes. A timing & responsibility plan for the required gauge equipment & fixtures, including ordering, certification & correlation of the gauging to ensure the completion prior to PPAP. Documented when the measurement will be taken process step, frequency, etc… Owner: Supplier
Note on B72: Gauge R&R and other customer requirements
Note on B73: Define which characteristics BW requires initial and or ongoing capability. Capability of each tooling, cavity, machine, etc must be consider when developing Measurement plan.
Note on B75: CQI-9 Heat Treat Assessment for all Heat Treatment operations (including Sub-Tier Suppliers)
Note on B76: BorgWarner & Supplier defined plan to achieve traceability of material
Note on B77: What: Documentation at the workstation required to ensure the process is well documented, the operator is trained, and process is maintained. This is a living document updated as lessons learned, Change Management, & Process experience is acquired. Action: Based on EPC Control Plan, process flow and PFMEA, the supplier develops Work/Process instructions as required Work/Process instructions should have adequate detail to ensure the operator can meet the quality expectations defined in the EPC control plan. Documented detailed work/process instructions typically include the following; Set-up Instructions Operations description Gauging instructions Maintenance plan (Tooling, Machine, etc) Training Plan for Operators Objective Evidence: On site verification or pictures of work station with visual instructions (job aids, boundary samples…etc) Review and timing of operator training plan This will be verified again during the WAR audit Owner: Supplier
Note on B83: What: Through actual packing & shipping evaluations, verify the product performance and characteristics remain unchanged during packing, shipping, storage, and material handling. Action: Supplier proposes packaging based on BW guidelines. Review any “lessons learned” on similar product, especially if shipping overseas Verification of the packing should include the representation from the BorgWarner receiving plant(s). This verification should include the following evaluations; - Dimensionally correct - Structural Integrity (shipping, loading, stack ability) - Part Preservation (prevents dents, scratches, rust, contamination, meets receiving plant regulatory requirements, etc) Objective Evidence: Packaging design & performance is approved by BW Owner: Supplier BW Packaging responsible individual
Note on B85: What: To ensure that the production process is capable at “full line speed” and identifies any weak points prior to full production. Action: Perform WAR audit to verify the production process produces a part meeting the quality requirements Perform Run @ Rate to verify production process meets BW Contracted capacity (not scheduled capacity) Perform Measurement Systems evaluations (Gage R&R) & confirm gage correlation between supplier & BW. These production process evaluations (WAR & Run @ Rate) must utilize: Production Equipment, Tooling. & Gauging Production Material Production Operators Production material handling systems Production location Using PPAP'd Sub-Tier material (The Run @ Rate process should be verified at critical sub-tier suppliers) Following the EPC Control Plan Parts from this production trail run are to be used to establish production capability and dimensional data for the PPAP submission Objective Evidence: Completed WAR audit with action plan to address any concerns/finding Confirmation of required capacity was met Acceptable Gage R&R (where applicable includes bias, stability, and linearity) & gage correlation studies Preliminary study on capability and dimensional layouts Sub-Tier PPAP submissions Owner: Supplier BW SDE verification on site when required
Note on B88: Verification all gages have acceptable gage R&R and where applicable this includes bias, stability, and linearity Correlation must be verified between Supplier & BW for all gages / measurement techniques
Note on B89: What: Statistical assessment of the manufacturing process to manufacture parts within specification limits Action: The supplier performs process capability studies based on the following Parts used in the evaluation are from the Production Trial run The Characteristics to be evaluated are based on: EPC control plan & other BW capability requirements defined during the APQP process (Measurement system plan) Borg Warner’s minimum required acceptance criteria for Special or Critical Characteristics are based on 100pc measurement study and a Cpk of 1.33 and Ppk of 1.67 unless otherwise agreed to. Any process not meeting these capability requirements MUST be either 100% inspected or pass through an approved Poke-Yoke Objective Evidence: Completed capability study with all designated characteristics meeting the requirements. Any characteristic not meeting these requirements must be contained by the following actions 100% inspection or error proofing installed Control plans & process instructions update to include the necessary guidance to ensure these containment actions are effective If the process is updated to comply with the capability requirements, then a new PPAP submission is required. Owner: Supplier Review by BW SDE
Note on B90: What: Production validation testing (PV) validates the Engineering Specification of production location, tooling, process, & operators Action: Using parts produced during the production trial run, the PV test plans are completed. The PV requirements should be identified on the print, within engineering specifications, or documented during the APQP kickoff Testing may be run at the supplier, at BW, at 3rd party, BW Customer or any combination of these Objective Evidence: PV test reports will be submitted to BW in the PPAP package Owner: Supplier Review and approved by BW Engineering & Customer when necessary
Note on B91: What: The validation of the suppliers ability to meet the customer engineering design and specifications requirements. Verifying the process has the potential to produce product consistently during an actual production trial run at the contracted rate unless otherwise agreed to by BorgWarner. Action: Based on the production trial run part, the customer submits all required documentation according to the BW PPAP Checklist (Form GSM-F005). The submitted documentation and parts (if required) are verified by appropriate BW personnel. All required PV results are confirmed acceptable BW designated representative reviews all the documentation and either reject the package or accept it by signing off on the warrant notifying the supplier of the status. If some of the items are not completed BW may grant an interim PPAP, with specific conditions identified. The supplier must submit and gain approval for a supplier deviation request (SDR) for any dimensional or performance characteristic not meeting the requirements. Objective Evidence: The approved warrant with all the necessary documentation Owner: Supplier BW SDE, Product Engineering, Quality
Note on B92: Timing of supplier submission of PPAP parts and all required supporting documentation (see PPAP check list)
Note on B93: Timing associated with BW PPAP verification & approval. This is to be defined by BW
Note on B94: What: The follow up and review of all the open issues documented on the We Are Ready (WAR) assessment Action: Verify all Red & Yellow action items have been closed Objective Evidence: Completed We Are Ready (WAR) assessment Owner: Supplier BW SDE
Note on B97: What: Verified capability to supply acceptable production parts Action: Verify all production controls are effective and process is released from EPC Boundary examples / Visual defect catalog(s) developed and agreed to EPC exit based on sustained I-Chart zero defect achieved for required period All part number CPM's Closed out Acceptable Delivery performance achieved Lessons learned are documented Objective Evidence: EPC Exit & Visual Defect catalog (if required) Delivery performance data CPM data Owner: Supplier BW SDE
Note on B47: Applicable if supplier is Design Responsible - Documented Performance or Design Specifications
Note on B49: Signed EPC Form to ensure Suppliers Sr. Management Awareness of need for Launch Controls. Additionally For resource or outsource projects: Prior to defining tooling and Gauging Plans -- Suppliers shall complete a Matrix to facilitate comparison of all current dimensions and tolerances, and comparison of gages used by the supplier and BorgWarner Plants.
Note on B50: All known / experienced defects (CPMS Data Base) on like product lines should be reviewed by Supplier & BorgWarner to facilitate development of APQP Action Plans that will ensure prevention, detection and or capability of processes to support Contain / Control.
Note on B55: What: A plan to review the evolving design to prevent problems and apply lessons learned Action: Supplier/BW will hold regular meetings to review design progress regardless of ownership Objective Evidence: Firm schedule for reviews – Included in the program timing chart Owner: Supplier Engineering (supplied design) BW Engineering (joint or provided design) APQP Team
Note on B80: Includes but not limited to: - Set-up Instructions - Operations description - Process / Work Instructions - Gauging instructions
Note on B79: Training plan should identify the following: 1) Skill set required 2) Timing Plan 3) Qty to be trained 4) Records of who is trained
Note on B86: Supplier Self assessment and (if required) BW on-site WAR audit performed and action plans documented addressing any concerns/finding
Note on B66: What: A review of all the objective evidence relative to the phase of the program being reviewed The Gate reviews are program milestones, and must be tracked to confirm program timing is maintained Action: All prior steps must be “Green” prior to gate sign off Action plans must be identified for any element not green, and elevated as necessary Team consensus is required but ultimately it’s the SDE who signs Objective Evidence: Gate review will be audited, based on BU specific requirements TS - TBD MT/TH - SSO Process Turbo Emissions - TBD TTS - TBD Owner: Supplier Development & BU auditor
Note on B81: What: A review of all the objective evidence relative to the phase of the program being reviewed The Gate reviews are program milestones, and must be tracked to confirm program timing is maintained Action: All prior steps must be “Green” prior to gate sign off Action plans must be identified for any element not green, and elevated as necessary Team consensus is required but ultimately it’s the SDE who signs Objective Evidence: Gate review will be audited, based on BU specific requirements TS - TBD MT/TH - SSO Process Turbo Emissions - TBD TTS - TBD Owner: Supplier Development & BU auditor
Note on B95: What: A review of all the objective evidence relative to the phase of the program being reviewed The Gate reviews are program milestones, and must be tracked to confirm program timing is maintained Action: All prior steps must be “Green” prior to gate sign off Action plans must be identified for any element not green, and elevated as necessary Team consensus is required but ultimately it’s the SDE who signs Objective Evidence: Gate review will be audited, based on BU specific requirements TS - TBD MT/TH - SSO Process Turbo Emissions - TBD TTS - TBD Owner: Supplier Development & BU auditor

## Open Issues
Open Issues - Action Plans
APQP Phase & Element | Date | Description of Concern | Actions Taken / Implemented | Name of Responsibility | Completion Date | Status
This is default form, alternative form may be used instead.

## Meeting Log
Meeting Log
Date of APQP Meetings
Name of Participant | Kick-off | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9
Optional Form

## Definitions
DEFINITIONS
controlled document in accordance to DIN ISO 9001 No. 4.2.3
ST |  | Solero Technologies
Risk/Status Assessment
Risk | Color | Definition
High | Red | Target dates and/or deliverables are at risk. A recovery work plan is not available and/or implemented, or the work plan does not achieve program targets.
Moderate | Yellow | Target dates and/or deliverables are at risk, but a resourced recovery work plan has been developed to achieve program targets, and has been approved by the appropriate Management Team
None | Green | Target dates and deliverables are on track and meeting objectives.
Form Requirements
Form |  |  | Process Required/Optional | Form Required/Optional
APQP |  |  | R | R
Open Issues |  |  | R | O
Meeting Log |  |  | O | O
Pass Through |  |  | O | O